Student Full Name:

Mónica Valenciano Barajas

Student Number:

2026556

Module Title:

Strategic Thinking

Assessment Title:

CA 1 – Capstone Project Proposal

Lecturer/Supervisor:

Mr. Taufique Ahmed

Assessment Due Date:

21-09-2026

Date of Submission:

25-10-2026

I acknowledge the use of Claude (Anthropic, 2026) for the purpose of obtaining guidance on how to cite websites, such as IMF PortWatch, using the Harvard referencing style, and for identifying reliable sources that explain this style.

Contents

1. Project Title	2

2. Introduction	2

3. Problem Definition	2

4. Aim and Objectives	2

5. Scope	3

6. Methodology	3

7. Data Sources	4

8. Expected Deliverables	4

9. Project Timeline	4

10. Ethical and Legal Considerations	5

References	6

Appendix	7

## 1. Project Title

Forecasting Workload Pressure in the European Union’s Largest Ports using IMF PortWatch Satellite Data

## 2. Introduction

Maritime transport is the foundation of trade. EU ports moved about 3.4 billion tonnes of freight in 2024 (Hellenic Shipping News, 2025) and the 20 biggest ports handled 49.8% of all EU port tonnage with Rotterdam alone handling 11.8% (Eurostat, 2025). When activity at these places increases suddenly ships wait in line schedules get delayed and costs go up for shipping companies, port workers and people who move goods. Official numbers come out months after the situation happens (Eurostat, 2025).

The IMF’s PortWatch now gives daily updates on port activity and trade estimates based on signals from, about 90,000 ships (IMF, 2026a; IMF, 2026c). This tool helps people see when ports might get busy before it happens.

## 3. Problem Definition

Ports and logistics planners do not have access to forward-looking information about how much work a port has. The demand for port services changes with seasons and can be affected by a variety of events and circumstances, which means, that sudden increases in activity can lead to docks and storage areas, delays and higher costs for moving goods. PortWatch does not provide information about waiting times, so the purpose of this project is create a way to measure this: a “high-load day” is when the number of ships arriving at a port in one day is more than the percentile of what is normally expected during that time of the year. A predictive modelling can help due to the port activity has patterns, seasonal changes and connections between ports, which time-series methods are good at understanding (Hyndman and Athanasopoulos, 2021). The basic numbers used in this project have been checked against records of ships arriving at ports in certain countries (Arslanalp et al., 2026), which shows that can be used as good inputs for the model.

## 4. Aim and Objectives

Aim: to create and test models that can predict workloads and busy days at the 20 biggest ports in the European Union. These models will use data from PortWatch from 2019 to 2026.

Objectives:

- Create a dataset for the 23 PortWatch ports that match the top 20 EU ports listed by Eurostat.

- Look at trends, changes, times of disruption and how ports affect each other.

- Compare forecasting methods using statical and machine-learning techniques for 7-day and 28-day predictions.

- Find out which days will have workloads and figure out what causes them.

- Provide a dashboard where people can see forecasts and get alerts about risks.

Hypothesis: models that use calendar information and data from ports will have a lower Mean Absolute Scaled Error than a basic seasonal model.

Business goal: help planners know about times up to four weeks, in advance.

## 5. Scope

Included: the 20 most important EU ports by tonnage (Eurostat, 2025) mapped to 23 Port Watch ports due to Antwerp-Bruges, HAROPA and Zeeland Seaports each combine two ports. The data covers records from 2019 to 2026. It includes port calls and estimated import and export volumes for each vessel type. Also included are forecasting tools, classification models and a dashboard for viewing the data.

Excluded: ports outside the EU like the UK, Türkiye and Norway. Real-time vessel tracking is not part of this. Neither is berth-level optimisation waiting-time modelling, causal economic analysis or commercial deployment. Semester 1 focuses on cleaning the data and setting up baseline models. Semester 2 moves on, to advanced models evaluating them and building the dashboard.

## 6. Methodology

The project follows the CRISP-DM framework (Chapman et al., 2000), a process for data projects. In terms the project moves through six steps:

1. Collect: gather the PortWatch data and the Eurostat port ranking.

2. Clean: correct missing days, remove mistakes and align port names across sources.

3. Prepare: transform numbers into useful clues for the models, such as the day of the week the season, recent activity and what is happening at nearby ports.

4. Predict: compare methods that repeat past patterns (seasonal naive, ETS and SARIMA; Box et al., 2015) with more advanced methods that learn complex patterns automatically: Prophet (Taylor and Letham, 2018), XGBoost (Chen and Guestrin, 2016) and LSTM neural networks (Hochreiter and Schmidhuber, 1997).

5. Test: ask each model to forecast periods it has not seen always moving forward in time so it never "peeks" at the future (Hyndman and Athanasopoulos, 2021). Measure errors with MASE and RMSE. Evaluate precision and recall seeing how well busy days are flagged.

6. Share: present the results, in a dashboard.

The tools are Python, Git and GitHub and Streamlit or Power BI chosen because they are widely used, reproducible and well documented. Figure 1 summarises the flow: data enter on the left are cleaned and prepared several models compete, testing selects the one and its forecasts appear on the dashboard.

| Data sources IMF PortWatch Daily Ports Data (2019–2026) and Eurostat (2025) top 20 ports | → | 1. Ingestion and storage Python, GitHub | → | 2. Cleaning and validation 23 ports | → | 3. Feature engineering Lags, calendar, cross-port signals |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | ↓ |
|  |  | 6. Dashboard 4-week forecasts and high-load alerts | ← | 5. Evaluation Rolling-origin CV; MASE, RMSE, F1 | ← | 4. Model training Seasonal naive, ETS/SARIMA, Prophet, XGBoost, LSTM |

Figure 1: Proposed workflow, from data sources to dashboard (read left to right, then right to left)

## 7. Data Sources

Primary source: IMF PortWatch Daily Ports Data (IMF, 2026a) covers 2,065 ports across the globe. Gets updated every week (IMF, 2026c). This source gives records of port arrivals and estimates of import and export volumes measured in metric tonnes for container, dry bulk and tanker ships (Arslanalp et al., 2026). If we narrow the focus to 23 ports and the years 2019 to 2026, we end up with about 65,000 port‑day entries, which's plenty for building and testing time‑series models.

Secondary source: Eurostat (2025) helps us pick ports based on how cargo they handle. Permission: IMF rules let us download, modify and publish the data long as we give credit and note any changes (IMF, 2026b). The data are free and available to the public.

## 8. Expected Deliverables

By the end of Semester 2, I will have cleaned and documented the dataset that includes a data dictionary. Also, I will have done some analysis looking at seasonality, disruptions and port clusters. Then, I will have benchmarked forecasting and classification models along with an evaluation report. There will be dashboard that shows four-week forecasts and alerts, for high-load periods. I will also have a GitHub repository that's easy to reproduce. Finally, I will have a report and a presentation.

## 9. Project Timeline

Figure 2 shows the eight‑month plan, and the plan has four months, in each semester and four milestones.

| Project activity | Semester 1 |  |  |  | Semester 2 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 |
| Data acquisition and permissions |  |  |  |  |  |  |  |  |
| Cleaning and validation |  |  |  |  |  |  |  |  |
| EDA and feature engineering |  |  |  |  |  |  |  |  |
| Baseline models (naive, ETS/SARIMA) |  |  |  |  |  |  |  |  |
| Advanced models (Prophet, XGBoost, LSTM) |  |  |  |  |  |  |  |  |
| Evaluation and robustness tests |  |  |  |  |  |  |  |  |
| Dashboard development |  |  |  |  |  |  |  |  |
| Final report and presentation |  |  |  |  |  |  |  |  |
| Milestones | ◆ |  |  | ◆ |  | ◆ |  | ◆ |

◆ Milestones: M1 dataset approved; M4 interim report; M6 best model chosen; M8 final submission.

Figure 2: Indicative project timeline (M = month; red diamonds = milestones)

## 10. Ethical and Legal Considerations

Privacy: PortWatch provides port-level estimates. No crew, passenger or personal information is included. Because of these GDPR obligations are not expected to apply. This will be confirmed during a data audit (European Union, 2016).

Permissions: The data will be used under the terms set by the IMF. Proper attribution will be. Any modifications will be clearly stated (IMF, 2026b). Since automated bulk downloading requires permission from the IMF files will be downloaded through the portal. The IMF will be contacted before using any API. Also, IMF content will not be used to train language models (IMF, 2026b).

Integrity: The estimates may. Be limited due to availability of AIS data (Arslanalp et al. 2026). As a result, forecasts will include uncertainty. Will not be presented as operationally certain.

Security: The GitHub repository will be private. It will only be shared with the lecturer. No credentials will be stored in the repository. The ethics form is submitted separately. AI use is declared in the accompanying document.

## References

- Arslanalp, S., Exton, O., Gao, C., Kamali, P., Saraiva, M., Sozzi, A. and Verschuur, J. (2026) Nowcasting country-level trade estimates using IMF PortWatch. IMF Working Paper WP/26/99. Washington, DC: International Monetary Fund. Available at: https://www.imf.org/-/media/files/publications/wp/2026/english/wpiea2026099-source-pdf.pdf (Accessed: 20 October 2026).

- Box, G.E.P., Jenkins, G.M., Reinsel, G.C. and Ljung, G.M. (2015) Time series analysis: forecasting and control. 5th edn. Hoboken, NJ: Wiley.

- Chapman, P., Clinton, J., Kerber, R., Khabaza, T., Reinartz, T., Shearer, C. and Wirth, R. (2000) CRISP-DM 1.0: step-by-step data mining guide. Chicago: SPSS Inc.

- Chen, T. and Guestrin, C. (2016) 'XGBoost: a scalable tree boosting system', in Proceedings of the 22nd ACM SIGKDD International Conference on Knowledge Discovery and Data Mining. San Francisco: ACM, pp. 785–794.

- European Union (2016) Regulation (EU) 2016/679 of the European Parliament and of the Council (General Data Protection Regulation). Official Journal of the European Union, L119, pp. 1–88. Available at: https://eur-lex.europa.eu/eli/reg/2016/679/oj (Accessed: 24 October 2026).

- Eurostat (2025) Maritime transport of goods – annual data. Statistics Explained. Available at: https://ec.europa.eu/eurostat/statistics-explained/index.php?title=Maritime_transport_of_goods_-_annual_data (Accessed: 21 October 2026).

- Hellenic Shipping News (2025) 'EU ports handled 3.4 bn tonnes of freight in 2024', 6 December. Available at: https://www.hellenicshippingnews.com/eu-ports-handled-3-4-bn-tonnes-of-freight-in-2024/ (Accessed: 24 October 2026).

- Hochreiter, S. and Schmidhuber, J. (1997) 'Long short-term memory', Neural Computation, 9(8), pp. 1735–1780.

- Hyndman, R.J. and Athanasopoulos, G. (2021) Forecasting: principles and practice. 3rd edn. Melbourne: OTexts. Available at: https://otexts.com/fpp3/ (Accessed: 24 October 2026).

- Hyndman, R.J. and Koehler, A.B. (2006) 'Another look at measures of forecast accuracy', International Journal of Forecasting, 22(4), pp. 679–688.

- IMF (2026a) PortWatch: Daily Ports Data. Available at: https://portwatch.imf.org/datasets/83b1bbc7b3354c5fb1f40673bb8f852e_0/explore (Accessed: 24 October 2026).

- IMF (2026b) Copyright and usage. Available at: https://www.imf.org/en/about/copyright-and-terms (Accessed: 15 October 2026).

- IMF (2026c) PortWatch: Data and methodology. Available at: https://portwatch.imf.org/pages/data-and-methodology (Accessed: 24 October 2026).

- Taylor, S.J. and Letham, B. (2018) 'Forecasting at scale', The American Statistician, 72(1), pp. 37–45.

## Appendix